## README
Program Plan & Cost Book: Two 5-Axis Machining Centers + Robotic Loading Cell
Mock customer program built as a project management portfolio piece. Customer and all figures are fictional and illustrative.
Scenario | Fictional customer Lakeshore Drivetrain Co. orders two 5-axis horizontal machining centers, two hydraulic fixture sets and a robotic loading cell to machine an aluminum transmission housing.
How to use | Blue text = inputs you can change. Black = formulas. Green = links from another tab. Yellow fill = key assumptions.
Schedule | Change durations, predecessors-driven start dates recalculate with WORKDAY. Gantt bars redraw from the dates.
Quote Build-up | Cost lines x markup = quoted price. Feeds the Cost Book budget.
Cost Book | Budget vs committed vs actual vs estimate-to-complete. EAC and variance calculate automatically.
Change Log | Customer change requests priced as supplementary quotes; approved ones roll into the revised contract on the Dashboard.
Risk Register | Probability x impact scoring with mitigation owners.
Runoff Checklist | Acceptance criteria checked at our plant and at the customer site.
Dashboard | One-page status for the customer program review: contract, margin, schedule health.

## Dashboard
Program Review Dashboard
Lakeshore Drivetrain Co. (fictional), two 5-axis machining centers + robotic loading cell
COMMERCIAL |  | SCHEDULE
Original contract value ($) | 2375922.3 | Status date | 2027-04-16
Approved change orders ($) | 24000 | Planned project finish | 2027-07-09
Revised contract value ($) | 2399922.3 | Overall % complete (duration-weighted) | 70.31%
Pending change orders ($) | 54300 | Tasks late | 1
Budget cost incl. approved COs ($) | 1969715 | Tasks in progress | 2
Estimate at completion ($) | 1958966 | Approved CO days (absorbed by float) | 5
Forecast margin ($) | 440956.3 | High risks open | 2
Quoted margin % | 17.88% | Runoff items passed (our plant) | 0 of 7
Forecast margin % | 18.37% | Overall status | AMBER: action needed
Margin change vs quote (pts) | 0.4983%
Talking points for program review
- Robot cell delivery is late; integration resequenced, expedite fee covered from contingency.
- Machine line is forecast over budget on the second spindle; contingency released to offset.
- CO-02 and CO-03 priced and sent as supplementary quotes; need customer decision before guarding work starts.

## Schedule
Project Schedule (Customer Time Schedule)
Start dates are driven by predecessors (finish-to-start, working days). Status is judged against the status date.
Project start | 2027-01-04 |  | Status date | 2027-04-16 |  | Holidays | 2027-05-31 | 2027-07-05
Gantt (week starting): dark blue = task, light = summary, orange = late, red = milestone
WBS | Task | Owner | Duration (days) | Predecessors | Start | Finish | % Complete | Status | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12 | 2027-04-19 | 2027-04-26 | 2027-05-03 | 2027-05-10 | 2027-05-17 | 2027-05-24 | 2027-05-31 | 2027-06-07 | 2027-06-14 | 2027-06-21 | 2027-06-28 | 2027-07-05 | 2027-07-12
1 | RFQ & Quotation |  | 21 |  | 2027-01-04 | 2027-02-01 | 100%
1.1 | Receive RFQ and SOW, log in quote tracker | Project Manager | 1 |  | 2027-01-04 | 2027-01-04 | 100% | Done
1.2 | Technical evaluation of scope (part, cycle time, tolerances) | Applications Engineer | 3 | 1.1 | 2027-01-05 | 2027-01-07 | 100% | Done
1.3 | Send clarification questions to customer | Project Manager | 2 | 1.2 | 2027-01-08 | 2027-01-11 | 100% | Done
1.4 | Build cost estimate in Quote Build-up | Project Manager | 4 | 1.3 | 2027-01-12 | 2027-01-15 | 100% | Done
1.5 | Internal quote review and approval | Sales Manager | 1 | 1.4 | 2027-01-18 | 2027-01-18 | 100% | Done
1.6 | Quote submitted to customer | Project Manager | 0 | 1.5 | 2027-01-18 | 2027-01-18 | 100% | Done
1.7 | Customer negotiation and PO | Sales Manager | 10 | 1.6 | 2027-01-19 | 2027-02-01 | 100% | Done
1.8 | Customer PO received | Project Manager | 0 | 1.7 | 2027-02-01 | 2027-02-01 | 100% | Done
2 | Order Release |  | 5 |  | 2027-02-02 | 2027-02-08 | 100%
2.1 | Scope-of-supply check: PO vs quote | Project Manager | 2 | 1.8 | 2027-02-02 | 2027-02-03 | 100% | Done
2.2 | Internal job order release | Project Manager | 0 | 2.1 | 2027-02-03 | 2027-02-03 | 100% | Done
2.3 | Issue customer time schedule | Project Manager | 2 | 2.2 | 2027-02-04 | 2027-02-05 | 100% | Done
2.4 | Kickoff meeting with customer | Project Manager | 1 | 2.3 | 2027-02-08 | 2027-02-08 | 100% | Done
3 | Engineering |  | 27 |  | 2027-02-04 | 2027-03-12 | 100%
3.1 | Fixture design (hydraulic, 2 sets) | Mechanical Design | 15 | 2.2 | 2027-02-04 | 2027-02-24 | 100% | Done
3.2 | Robot cell layout and guarding design | Automation Engineer | 15 | 2.2 | 2027-02-04 | 2027-02-24 | 100% | Done
3.3 | CNC process and program development | Applications Engineer | 12 | 3.1 | 2027-02-25 | 2027-03-12 | 100% | Done
3.4 | Customer design review approved | Project Manager | 0 | 3.1, 3.2 | 2027-02-24 | 2027-02-24 | 100% | Done
4 | Procurement |  | 45 |  | 2027-02-04 | 2027-04-07 | 91.67%
4.1 | Long-lead items: spindles and CNC controls | Purchasing | 40 | 2.2 | 2027-02-04 | 2027-03-31 | 100% | Done
4.2 | Robot and safety guarding | Purchasing | 30 | 3.4 | 2027-02-25 | 2027-04-07 | 75% | LATE
4.3 | Fixture components | Purchasing | 20 | 3.4 | 2027-02-25 | 2027-03-24 | 100% | Done
5 | Build & Assembly |  | 37 |  | 2027-03-25 | 2027-05-14 | 49.84%
5.1 | Machine 1 assembly | Assembly | 20 | 4.1 | 2027-04-01 | 2027-04-28 | 55% | In progress
5.2 | Machine 2 assembly | Assembly | 22 | 4.1 | 2027-04-01 | 2027-04-30 | 45% | In progress
5.3 | Fixture build and CMM inspection | Quality | 10 | 4.3 | 2027-03-25 | 2027-04-07 | 100% | Done
5.4 | Cell integration and controls I/O check | Controls Engineer | 10 | 5.1, 5.2, 5.3, 4.2 | 2027-05-03 | 2027-05-14 | 0% | Not started
6 | Runoff & Acceptance |  | 8 |  | 2027-05-17 | 2027-05-26 | 0%
6.1 | Internal quality check against runoff checklist | Quality | 3 | 5.4 | 2027-05-17 | 2027-05-19 | 0% | Not started
6.2 | Pre-acceptance runoff at our plant (Cpk study) | Applications Engineer | 5 | 6.1, 3.3 | 2027-05-20 | 2027-05-26 | 0% | Not started
6.3 | Customer buy-off signed | Project Manager | 0 | 6.2 | 2027-05-26 | 2027-05-26 | 0% | Not started
7 | Delivery & Installation |  | 25 |  | 2027-05-27 | 2027-07-01 | 0%
7.1 | Teardown, crate and ship | Logistics | 7 | 6.3 | 2027-05-27 | 2027-06-07 | 0% | Not started
7.2 | Installation and leveling at customer site | Service | 10 | 7.1 | 2027-06-08 | 2027-06-21 | 0% | Not started
7.3 | Final runoff at customer site | Applications Engineer | 5 | 7.2 | 2027-06-22 | 2027-06-28 | 0% | Not started
7.4 | Operator and maintenance training | Service | 3 | 7.3 | 2027-06-29 | 2027-07-01 | 0% | Not started
7.5 | Final acceptance | Project Manager | 0 | 7.4 | 2027-07-01 | 2027-07-01 | 0% | Not started
8 | Closeout |  | 5 |  | 2027-07-02 | 2027-07-09 | 0%
8.1 | Final cost book reconciliation | Project Manager | 3 | 7.5 | 2027-07-02 | 2027-07-07 | 0% | Not started
8.2 | Lessons learned and handover to service | Project Manager | 2 | 8.1 | 2027-07-08 | 2027-07-09 | 0% | Not started
8.3 | Project closed | Project Manager | 0 | 8.2 | 2027-07-09 | 2027-07-09 | 0% | Not started

## Quote Build-up
Quote Build-up (RFQ response)
Cost estimate per scope line, marked up to the quoted sell price. Quantities, unit costs and markups are inputs.
Default markup |  | 22% | Assumption: markup on cost (22% markup = about 18% margin on sell price); illustrative.
Line | Scope item | Unit | Qty | Unit cost ($) | Cost ($) | Markup | Sell price ($)
Machine | 5-axis horizontal machining center (base machine) | ea | 2 | 620000 | 1240000 | 22% | 1512800
Fixture | Hydraulic fixture set, single nest | set | 2 | 47500 | 95000 | 22% | 115900
Automation | Robotic loading cell incl. safety guarding | lot | 1 | 180000 | 180000 | 22% | 219600
Controls | Controls and software integration | lot | 1 | 45000 | 45000 | 22% | 54900
Eng labor | Engineering hours (mech, controls, apps) | hr | 900 | 95 | 85500 | 22% | 104310
Assy labor | Assembly hours | hr | 1400 | 70 | 98000 | 22% | 119560
Runoff | Runoff and applications support | hr | 240 | 95 | 22800 | 22% | 27816
Freight | Freight, crating and rigging | lot | 1 | 38000 | 38000 | 10% | 41800
Install | Installation and travel | lot | 1 | 42000 | 42000 | 22% | 51240
Training | Operator and maintenance training | lot | 1 | 12000 | 12000 | 22% | 14640
| Warranty reserve (% of cost) |  | 2% |  | 37166 | 22% | 45342.52
| Contingency (% of cost) |  | 3% |  | 55749 | 22% | 68013.78
| TOTAL |  |  |  | 1951215 |  | 2375922.3
| Quoted margin | [5 empty] | 17.88%

## Cost Book
Project Cost Book
Budget comes from the quote. Committed = POs placed. Actual = invoiced/booked to date. ETC = estimate to complete. EAC = Actual + ETC.
Line | Cost item | Budget ($) | Committed ($) | Actual to date ($) | Est. to complete ($) | EAC ($) | Variance ($) | Variance % | Note
Machine | 5-axis horizontal machining center (base machine) | 1240000 | 1250000 | 610000 | 640000 | 1250000 | -10000 | -0.8065% | Machine 2 spindle quote came in higher
Fixture | Hydraulic fixture set, single nest | 95000 | 95000 | 88000 | 7000 | 95000 | 0 | 0%
Automation | Robotic loading cell incl. safety guarding | 180000 | 186500 | 140000 | 46500 | 186500 | -6500 | -3.611% | Robot delivery 1 week late; expedite fee
Controls | Controls and software integration | 45000 | 30000 | 12000 | 33000 | 45000 | 0 | 0%
Eng labor | Engineering hours (mech, controls, apps) | 85500 | 0 | 71000 | 16000 | 87000 | -1500 | -1.754% | Hours tracked from timesheets
Assy labor | Assembly hours | 98000 | 0 | 52000 | 48000 | 100000 | -2000 | -2.041%
Runoff | Runoff and applications support | 22800 | 0 | 0 | 22800 | 22800 | 0 | 0%
Freight | Freight, crating and rigging | 38000 | 0 | 0 | 38000 | 38000 | 0 | 0%
Install | Installation and travel | 42000 | 0 | 0 | 42000 | 42000 | 0 | 0%
Training | Operator and maintenance training | 12000 | 0 | 0 | 12000 | 12000 | 0 | 0%
Warranty | Warranty reserve (% of cost) | 37166 | 0 | 0 | 37166 | 37166 | 0 | 0% | Held until warranty period ends
Contingency | Contingency (% of cost) | 55749 | 0 | 0 | 25000 | 25000 | 30749 | 55.16% | Partly released to absorb machine and robot overruns; $25k held for install risk
| TOTAL | 1951215 | 1561500 | 973000 | 967466 | 1940466 | 10749 | 0.5509%
Variance = Budget - EAC. Negative (red) means the line is forecast over budget.

## Change Log
Change Log and Supplementary Quotes
Every customer change is priced as a supplementary quote. Only Approved changes count toward the revised contract.
CO # | Description | Requested by | Date | Added cost ($) | Supplementary quote ($) | Schedule impact (days) | Status
CO-01 | Add part variant B: second nest on each fixture, new CNC program (absorbed by fixture float) | Customer | 2027-03-02 | 18500 | 24000 | 5 | Approved
CO-02 | Spare spindle cartridge for customer stock | Customer | 2027-04-09 | 32000 | 41600 | 0 | Pending
CO-03 | Upgrade guarding to customer corporate safety standard | Customer | 2027-04-14 | 9800 | 12700 | 3 | Pending
| Approved total |  |  | 18500 | 24000 | 5
| Pending total |  |  | 41800 | 54300

## Risk Register
Risk Register
Probability and impact on a 1-5 scale. Score = P x I. 15+ is high, 8-14 medium.
ID | Risk | Probability (1-5) | Impact (1-5) | Score | Rating | Mitigation | Owner
R1 | Long-lead spindle or control delivery slips | 3 | 5 | 15 | High | Order at job release; weekly supplier check-in; track in schedule | Purchasing
R2 | Part fails Cpk 1.33 at runoff | 2 | 5 | 10 | Medium | Early capability trial on machine 1; fixture CMM check before runoff | Applications Engineer
R3 | Customer scope creep without paperwork | 4 | 3 | 12 | Medium | Every change through Change Log and supplementary quote before work starts | Project Manager
R4 | Robot cell delivery late (now happening) | 5 | 3 | 15 | High | Expedite fee budgeted from contingency; resequence integration | Project Manager
R5 | Site not ready for install (foundation, power, air) | 2 | 4 | 8 | Medium | Send site-prep checklist 8 weeks before ship; confirm at program review | Service

## Runoff Checklist
Runoff Checklist
Acceptance criteria agreed with the customer at order. Pre-acceptance at our plant, final at customer site.
# | Check | Requirement | Method | Our plant | Customer site
1 | Cycle time per part | <= 4.5 min | Timed 30-part run | Open | Open
2 | Process capability, critical bores | Cpk >= 1.33 | CMM, 30 consecutive parts | Open | Open
3 | Position tolerance, bolt pattern | Per drawing, datums A¦B¦C | CMM report | Open | Open
4 | Unattended run | 4 hours, no stops | Robot cell continuous run | Open | Open
5 | Safety guarding and interlocks | Customer safety standard | Interlock test sheet | Open | Open
6 | Documentation package | Manuals, electrical prints, spares list | Checklist sign-off | Open | Open
7 | Operator training | 2 shifts trained | Attendance sign-off | Open | Open
| Items passed at our plant |  |  | 0 of 7